Project Management Plan

Amazon Farm Fresh

Version 1.4

CPSC8820-03 SP2024 Group 2

Amazon Farm Fresh

Koramangala 4th Street

Bangalore City, KARNATAKA, 560034

04/14/25

Revision History

|  |  |  |  |
| --- | --- | --- | --- |
| Rev | Date | Purpose | Originator |
| V.1 | 02-23-2024 | First draft: Containing Executive Summary, Project Charter & Project Scope Management Plan | Ashish Sai Thalla  Mounish Kanderi Murali  Chandana Chavatapalem  Ramu Yanamalachintala |
| V.2 | 3/10/2024 | This plan incorporates feedback from PMP1.0 and adds Schedule management plan and Cost management plan | Ashish Sai Thalla  Mounish Kanderi Murali  Chandana Chavatapalem  Ramu Yanamalachintala |
| V.3.1 | 4/22/2024 | This Plan includes feedback from PMP 1.12 and add Staffing management Plan & Risk Register & Quality Management | Ashish Sai Thalla  Mounish Kanderi Murali  Chandana Chavatapalem  Ramu Yanamalachintala |
| V.4 | 4/22/2024 | This plan contains updated changes to the Stake holder management plan, Communication Management Plan and Risk Register . | Ashish Sai Thalla  Mounish Kanderi Murali  Chandana Chavatapalem  Ramu Yanamalachintala |
|  |  |  |  |

Table of Contents

[1. Executive Summary 1](#_Toc164647952)

[2. Project Charter 2](#_Toc164647953)

[3. Scope Management Plan please keep consistent size font for this section 3](#_Toc164647954)

[3.1 Introduction 3](#_Toc164647955)

[3.2 Project Scope Statement 4](#_Toc164647956)

[3.3 User Story 1](#_Toc164647957)

[3.4 Scope Validation 12](#_Toc164647958)

[3.5 Managing Requests for Changes to Project Scope 12](#_Toc164647959)

[4. Schedule Management Plan 13](#_Toc164647960)

[4.1 Plan Schedule Management 13](#_Toc164647961)

[4.2 Activities Estimation 15](#_Toc164647962)

[4.3 Develop Schedule 17](#_Toc164647963)

[4.3.1 Sprint Schedule 17](#_Toc164647964)

[4.3.2 Gantt Chart 19](#_Toc164647965)

[4.4 Control Schedule 20](#_Toc164647966)

[4.5 Level Of Accuracy 22](#_Toc164647967)

[4.6 Control Thresholds 22](#_Toc164647968)

[4.7 Rules Of Performance Measurement 22](#_Toc164647969)

[4.8 Reporting Frequency and Formats 22](#_Toc164647970)

[5. Project Cost Management Plan 22](#_Toc164647971)

[5.1 Purpose 22](#_Toc164647972)

[5.2 Cost Management Planning 22](#_Toc164647973)

[5.3 Cost Estimation 23](#_Toc164647974)

[5.4 Cost Budgeting 26](#_Toc164647975)

[5.5 Cost Control 27](#_Toc164647976)

[6. Project Staffing Management Plan 28](#_Toc164647977)

[6.1 Organization Chart 31](#_Toc164647978)

[6.2 Resource Histogram 32](#_Toc164647979)

[7. Quality Management Plan 33](#_Toc164647980)

[7.1 Quality Objective 33](#_Toc164647981)

[7.2 Quality Management Planning 33](#_Toc164647982)

[7.2.1 Key Quality Areas & Metrics 34](#_Toc164647983)

[7.3 Quality Managing 35](#_Toc164647984)

[7.4 Quality Controlling 36](#_Toc164647985)

[7.5 Testing Methods 36](#_Toc164647986)

[7.6 Problem Reporting & Correction 37](#_Toc164647987)

[8. Risk Management Plan 39](#_Toc164647988)

[8.1 Risk Register for Amazon Fresh Project 39](#_Toc164647989)

[9. Communication Management Plan 42](#_Toc164647990)

[9.1 Stakeholder Communication Requirements 42](#_Toc164647991)

[9.2 Communication Summary 44](#_Toc164647992)

# Executive Summary

Amazon Fresh's development of a mobile-first online grocery platform customized for the Indian market reflects strategic acumen. It leverages the country's rapid digitalization and widespread mobile usage to align with both India's vision of a digital economy and the growing consumer demand for convenience. Prioritization of intuitive mobile experience, multilingual interfaces, and integration with local payment methods aims to establish Amazon Fresh as the preferred choice for online grocery shopping throughout India.

Amazon Fresh targets its expansion into India's less-saturated secondary markets where existing players such as BigBasket, BBdaily, Flipkart, and Grofers have faced obstacles. These challenges include logistical hurdles, catering to regional consumer preferences, and optimizing supply chains. Amazon Fresh aims to overcome these by harnessing its technological expertise, robust logistics network, and commitment to a deeply localized customer experience.

The timing of Amazon Fresh's initiative coincides with India's increasing digital literacy and mobile penetration beyond major urban centers. This burgeoning digital landscape provides a ready-made audience for Amazon Fresh's advanced mobile and web applications in emerging markets. A mobile-first approach addresses network constraints, ensuring a seamless, user-friendly experience for India's growing base of digitally savvy consumers.

**Key Strategic Differentiators**

Amazon Fresh stands apart with its focus on integrating local farmers and suppliers directly into its supply chain. This "farm to table" strategy benefits the regional economy and establishes a competitive edge through guaranteed freshness – a key consumer concern. Forging these local alliances will help Amazon Fresh resolve the complex logistical bottlenecks that have hindered its competitors.

Amazon Fresh's approach acknowledges that consumers in secondary markets may still favor traditional shopping methods. To address this, Amazon Fresh offers a deeply customized experience:

* **Multilingual Support:** A multilingual interface minimizes language barriers and promotes inclusivity.
* **Payment Flexibility:** Integrating popular digital wallets, UPI, and traditional payment methods increases accessibility.
* **Localized Marketing:** Tailored marketing campaigns build brand trust and resonate with regional consumers.

**Expansion Strategy and Building Competitive Advantage**

Amazon Fresh recognizes the need for strategic investments in logistics and infrastructure tailored to these new markets. Learning from competitors' challenges enables Amazon Fresh to strive for a first-mover advantage in many of these regions, establishing strong customer loyalty and a dominant market presence.

**Commitment to Growth and Regulatory Compliance**

Amazon Fresh's expansion promises not only to transform the online grocery landscape but also contribute meaningfully to the digital and economic advancement of developing urban centers across India. This aligns with Amazon's global expansion goals. The company will collaborate closely with its legal and compliance teams to ensure alignment with the evolving regulatory landscape of Indian e-commerce, paying close attention to data protection protocols.

# Project Charter

|  |
| --- |
| Project Title: Amazon Fresh Mobile App Development & India Launch  Date of Authorization: 02/15/2024  Project Start Date: 02/18/2024 Project End Date : 08/11/ 2025 |
| Key Schedule Milestones:   * Market Analysis & Requirements Gathering: 04/10/2024 * App Design (UX/UI) Completion: 05/13/2024 * Core Feature Development: 07/05/2024 * Alpha Testing & QA: 08/08/2024 * India Market Beta Launch: 09/11/2024 * Full-Scale India Launch: 10/14/2024 |
| Budget Information: $1.5 million. This project aligns with Amazon's strategic expansion goals and aims to drive significant market share growth within the Indian online grocery sector. |
| Project Manager: Mounish Kanderi Murali   |  |  |  |  | | --- | --- | --- | --- | | **Name** | **Role** | **Level** | **Email** | | Mounish Kanderi | Project Manager | Manager | mkanderi@amazon.com | | Ramu Yanamalachintala | Program Director | Director | ryanamalachintala@amazon.com | | Chandana Chavatapalem | Quality Assurance Lead | Manager | cchavatapalem@amazon.com | | Ashish Sai Thalla | Logistics & Supply Chain Lead | Manager | athalla@amazon.com | | Priya Singh | India Market Strategist | Manager | psingh@amazon.com | | Arjun Patel | UX/UI Design Lead | Manager | apatel@amazon.com | | Kavita Rao | Lead App Developer | Manager | krao@amazon.com | | Ravi Kumar | India Business Unit Liaison | Director | rkumar@amazon.com | |
| Project Objectives:   * Develop a cutting-edge mobile application (Android & iOS) for Amazon Fresh tailored to the unique demands of the Indian market. * Prioritize a seamless user experience on smartphones, optimize the app for varying network conditions. * Integrate AI-powered product recommendations to personalize the shopping experience. * Partner with local farmers and suppliers for direct sourcing and freshness (Farm to Table concept). * Localize the app with multilingual interfaces and support for diverse Indian payment options. |
| Project Success Criteria: very nice!   * Market Penetration: Achieve 5% market share within the first year of launch. * User Adoption: 1 million app downloads and 500,000 active users within the first six months. * App Performance: Ensure smooth functionality, quick load times, and minimal crashes even in low-bandwidth areas. * Customer Satisfaction: Achieve an average user rating exceeding 4 stars on app stores. * Positive Reviews: Garner predominantly positive online sentiment and media coverage for the app. |
| Approach: I like this!   * Agile Methodology: Use iterative development for flexibility and responsiveness to Indian market feedback. * User-Centric Design: Focus intensely on intuitive navigation and features prioritized by the Indian consumer. * Localization: Work with cultural experts for language translations, payment method choices, and marketing that resonates. * Robust Testing: Conduct rigorous testing on various devices and network speeds common to India. |
| Risk Management:   * Competitive Landscape: Existing players like BigBasket, Grofers, etc. pose stiff competition. * Cultural Barriers: Adoption of the app may be hindered by cultural differences. * Logistics: Efficient and reliable delivery in tier 2 cities is a challenge. |
| Sign-Off: (Signatures of Key Stakeholders) |
| Comments:  *"The beta launch and full-scale launch dates seem aggressive. Can we explore a phased rollout to manage risk and incorporate early feedback?"* - Program Director ☺ good comments!  *"These dates align well with Diwali and other major Indian festivals. Let's ensure our marketing team capitalizes on these peak shopping periods."* - India Business Unit Liaison ☺ cute! Sounds like business marketing folks. |

# Scope Management Plan please keep consistent size font for this section

## Introduction

The Scope Management Plan for the Amazon Fresh Mobile App Development & India Launch project outlines the processes and strategies to ensure the project's objectives are clearly defined, validated, and managed throughout its lifecycle. This plan incorporates comprehensive methodologies for defining product scope, validating scope through user and functionality testing, and managing scope changes with a structured change control process. It emphasizes the alignment with Agile Software Development Life Cycle (SDLC) principles, particularly the utilization of user stories for detailed requirement documentation and scope delineation.

## Project Scope Statement

Project Scope Statement

* **Product Scope Description:** The objective is to develop and launch a mobile-first online grocery platform for the Indian market, optimized for tier 2 cities. This platform will integrate local supply chains, offer personalized shopping experiences, and support diverse payment methods, aiming to establish Amazon Fresh as the premier online grocery service in India.
* **Product User Acceptance Criteria:** High usability scores, fulfillment of personalized recommendation accuracy, seamless integration of payment methods, and adherence to local e-commerce regulations and data privacy requirements.
* **Project Deliverables:** A fully functional mobile application on Android and iOS, backend infrastructure for order management and delivery logistics, and partnerships with local farmers and suppliers.
* **Project Boundaries, Constraints, and Assumptions:** The project will operate within the regulatory framework of Indian e-commerce and data privacy laws. It assumes a stable internet infrastructure in tier 2 cities and willingness of local suppliers to partner with Amazon Fresh.
* **Supporting Document References:** Project charter, market analysis reports, previous Amazon Fresh project documentation, and Indian e-commerce policy guidelines.

## User Story

|  |  |  |  |
| --- | --- | --- | --- |
| User Story # | Title | User Stories & Acceptance Criteria | Tasks |
| US01 | Account Registration | As a new user, I want to register for an Amazon Fresh account so that I can start using the service.  **Acceptance Criteria:**   1. The app provides an option for new users to register for an Amazon Fresh account. 2. The registration process asks for essential information (e.g., name, email, mobile number). 3. Users can set a password for their new Amazon Fresh account. 4. After successful registration, the user receives a confirmation email or SMS. 5. The app redirects the user to the login page to sign in with their new credentials. | **Tasks:**   * Design the registration form. * Implement backend support for user registration. * Set up email/SMS confirmation services. |
| US02 | Existing Account Login | As a user with an Amazon account, I want to use my Amazon credentials to log in so that I do not have to create a new account.  **Acceptance Criteria:**   1. The login page offers an option to sign in using an existing Amazon account. 2. Users can enter their Amazon account credentials (email/phone and password). 3. Authentication is securely handled, and upon success, users are logged into Amazon Fresh. 4. If the authentication fails, users receive an error message with the option to retry or reset their password. 5. First-time Amazon Fresh users are prompted to confirm or update their delivery information after logging in. | **Tasks:**   * Implement an authentication system that integrates with Amazon's existing account management. * Design a seamless login flow for users with existing Amazon accounts. * Ensure secure handling of user credentials and personal information. |
| US03 | Auto Language Setting | As a user, I want the app to set the language based on my location so that I can navigate it in my preferred language.  **Acceptance Criteria:**   1. Upon first login or registration, the app requests permission to access the user's location. 2. If the user grants permission, the app detects the user's location and sets the language based on the predominant language of that region. 3. If the user denies location access, the app defaults to English or allows the user to manually select their preferred language. 4. Users can change their language preference at any time through the app settings. 5. The language setting applies to all app content, including menus, product descriptions, and customer support. | **Tasks:**   * Implement location detection functionality. * Map regions to their predominant languages. * Design a user interface for language selection and adjustment. |
| US04 | Personalized Display | As a logged-in user, I want products to be populated based on my location so that I can see relevant items and offers.  **Acceptance Criteria:**   1. Once logged in, the app automatically populates products based on the user's current location. 2. The product selection includes region-specific offers and promotions. 3. Popular products in the user's region are highlighted or featured prominently on the home screen or dedicated sections. 4. If the app cannot determine the user's location (or if location permissions are denied), it defaults to displaying generic popular products and offers. 5. Users have the option to manually set or change their location to see products from different regions. | **Tasks:**   * Integrate a location-based filtering mechanism for product listings. * Develop a system to manage and display region-specific offers and promotions. * Implement a feature to highlight popular products based on regional sales data. * Create a fallback mechanism for product display when location data is unavailable. |
| US05 | Location-Based Offers | As a user, I want to see offers that are specific to my location so that I can take advantage of local deals.  **Acceptance Criteria:**   1. The app displays offers and promotions based on the user's confirmed or set location. 2. Location-based offers are updated in real-time to reflect current promotions and discounts. 3. Users can access a dedicated section or tab within the app that lists all current location-specific offers. 4. Notifications for new offers and promotions can be enabled based on the user's preference, with the ability to opt-in for location-specific alerts. 5. The app provides an easy way for users to share offers with friends and family, potentially increasing app engagement. | **Tasks:**   * Design and implement a dynamic content system for managing and displaying location-specific offers. * Enable real-time updates and notifications for relevant offers. * Provide users with customization options for receiving offer notifications. |
| US06 | Popular Local Products | As a logged-in user, I want to see popular products in my region so that I can discover what's trending nearby.  **Acceptance Criteria:**   1. Popular products in the user's location are identified based on sales data and customer preferences. 2. These products are featured in a dedicated section, such as "Popular in Your Area," on the home page or within the app. 3. The selection of popular products is regularly updated to reflect current trends and seasonal demands. 4. Users can view details, reviews, and ratings for these popular products to make informed purchasing decisions. 5. The feature takes into account the user's past purchases and preferences to further personalize the selection of highlighted products. | Tasks:   * Analyze sales and customer data to identify popular products by region. * Implement a system for dynamically updating and displaying these products in the app. * Ensure that product details, including reviews and ratings, are easily accessible to users. |
| US07 | Festival Offers | As a user, I want the app to showcase festival-related products so that I can participate in local celebrations.  **Acceptance Criteria:**   1. The app identifies upcoming local festivals based on the user's location and the regional cultural calendar. 2. Special promotions, discounts, and products related to these festivals are prominently displayed in a dedicated section, such as "Festival Offers" or "Celebrate with Amazon Fresh." 3. The festival-related product offerings include items commonly used for celebrations, such as decorations, traditional foods, and gift options. 4. The app provides detailed information about the significance of each festival, including how it's traditionally celebrated, to educate users and enhance their shopping experience. 5. Users receive notifications about upcoming festival offers, allowing them to prepare and shop in advance. | **Tasks:**   * Integrate a regional cultural calendar to track local festivals. * Curate festival-specific product lists and offers in collaboration with suppliers. * Design an informational section to educate users about each festival's traditions and significance. * Implement a notification system for upcoming festivals and related offers. |
| US08 | Popular Festival Items | As a user, I want to see popular festival products for my region so that I can make informed purchases for celebrations.  **Acceptance Criteria:**   1. A section within the app, "Popular Festival Picks," features products popular during specific local festivals, updated according to the cultural calendar. 2. This section updates automatically as different festivals approach, highlighting relevant items such as special foods, clothing, and decorations. 3. Products featured in the "Popular Festival Picks" are based on historical sales data during similar past festivals and anticipated trends. 4. User reviews and ratings for these products are easily accessible, providing insights into product quality and satisfaction. 5. Users can filter the popular festival products by categories, such as sweets, decorations, and gifts, for easier navigation. | **Tasks:**   * Analyze historical sales data to identify popular products for each festival. * Update the product display system to feature festival-specific popular items. * Enable filtering options for the "Popular Festival Picks" section. |
| US09 | Festival Recommendations | As a logged-in user, I want to receive personalized recommendations for festivals so that I can quickly find items for festival preparations.  **Acceptance Criteria:**   1. The app uses an AI-driven recommendation engine to suggest festival-related products tailored to the user's preferences and past shopping behavior. 2. Recommendations include a mix of traditional and modern items relevant to the upcoming local festival, ensuring a broad selection that appeals to diverse tastes. 3. The app allows users to provide feedback on recommendations, refining the personalization engine over time. 4. Personalized festival shopping lists or carts can be saved and shared with friends and family, encouraging collaborative celebration planning. 5. Users have the option to opt-in for personalized festival shopping reminders and recommendations via app notifications or email. | **Tasks:**   * Enhance the recommendation engine to incorporate festival-related factors and user preferences. * Implement a feedback loop for users to refine recommendation accuracy. * Develop functionality for creating, saving, and sharing personalized festival shopping lists. |
| US10 | Enhanced Search | As a user, I want an intuitive search feature with sorting so that I can find and sort products easily.  **Acceptance Criteria:**   1. The app provides a robust search feature that allows users to input search queries for products or categories. 2. Search results can be sorted by various criteria, including price (low to high, high to low), popularity, customer ratings, and relevance to the search query. 3. The search interface includes filters for brand, price range, product type, and other relevant categories to refine search results further. 4. Auto-suggestions are provided as the user types their search query to help quickly identify possible search intentions. 5. Search results are displayed in an easy-to-navigate format, with clear product information and the option to sort according to the selected criteria. 6. The app remembers the user's last sorting preference and applies it to future searches until changed. | **Tasks:**   * Implement a search engine within the app that can handle complex queries and return relevant results. * Develop a sorting algorithm that reorders search results based on selected criteria. * Design and integrate an auto-suggestion feature that activates during user input in the search bar. * Create a user-friendly interface for search results, incorporating sorting and filtering options. * Ensure the app's backend can remember and apply the user's last sorting preference for subsequent searches. |
| US 11 | Add Quantity to Cart | As a user, I want to select the desired quantity before adding to my cart so that I purchase the right amount.  **Acceptance Criteria:**   1. Each product page includes an option for users to select or input the desired quantity before adding the item to their cart. 2. The selected quantity is clearly displayed in the cart summary, allowing for easy review and adjustments if necessary. 3. The app prevents users from selecting a quantity beyond the available stock, displaying a message if the desired quantity exceeds current inventory levels. 4. Updates to product quantities within the cart are intuitive, with options to increase, decrease, or remove items directly from the cart interface. 5. The system updates the cart's total cost in real-time as quantities are adjusted. | **Tasks:**   * Design and implement a quantity selector on product pages. * Ensure cart summary accurately reflects changes in product quantities. * Implement inventory checks to prevent selection of unavailable quantities. * Allow for easy quantity adjustments within the cart. |
| US 12 | Out-of-Stock Alerts | As a user, I want to be notified if a product is out of stock so that I can purchase it when available.  **Acceptance Criteria:**   1. If a product is out of stock, the app offers an option to "Notify Me When Available." 2. Users opting for notifications provide a preferred method of contact (app notification, email, or SMS). 3. When the product is restocked, users receive a timely notification through their selected contact method. 4. The notification includes a direct link to the product page for easy access and purchase. 5. Users have the option to manage their notification preferences and cancel alerts for specific products through the app settings. | **Tasks:**   * Implement an "Notify Me When Available" feature for out-of-stock products. * Develop a system for tracking user requests for product availability notifications. * Set up notification delivery mechanisms via app notifications, email, and SMS. * Ensure direct links to product pages are included in restock alerts for convenience. |
| US 13 | Flexible Payments | As a user, I want to choose from a variety of payment methods so that I can use my preferred payment method.  **Acceptance Criteria:**   1. During the checkout process, users are presented with a comprehensive list of payment options, including credit/debit cards, digital wallets (e.g., Amazon Pay), UPI IDs, GPay, Paytm, cash on delivery (COD), and card on delivery. 2. Users can select their preferred payment method and provide the necessary details for processing (e.g., card number for credit/debit card, UPI ID for UPI payments). 3. For digital wallet options, the app facilitates seamless integration, allowing users to authorize payment directly within the app. 4. For COD and card on delivery options, users are informed about any additional terms or conditions (e.g., availability based on location, maximum order value). 5. The app securely saves user payment preferences for future transactions, offering the option to easily select a previously used method. 6. Users have the ability to change their payment method before finalizing the order if they decide against their initial choice. | **Tasks:**   * Integrate multiple payment gateways to support a variety of payment methods. * Implement a user interface for selecting and inputting payment details for the chosen method. * Ensure secure handling and storage of payment information in compliance with PCI DSS and other relevant data protection regulations. * Develop backend logic to handle different payment workflows, including real-time transactions for digital payments and order finalization for COD/card on delivery. |
| US 14 | Modify Delivery Address | As a user, I want to modify my delivery address before delivery so that my order is delivered to the correct location.  **Acceptance Criteria:**   1. Users can access their order history and select an order that is in a status that allows for address modification (e.g., ordered but not yet shipped). 2. Upon selecting the order, users are provided an option to "Change Delivery Address" if the order's current status permits modifications. 3. The app presents a form for users to enter a new delivery address or select from previously saved addresses. 4. After submitting the new address, users receive a confirmation of the address change via their preferred method of communication (app notification, email, SMS). 5. The app clearly informs users of any potential delays or changes in delivery charges resulting from the address change. 6. If an order's status does not permit address changes (e.g., order already shipped), the app informs the user and provides options for customer support. | **Tasks:**   * Implement functionality within the order history section to allow address modifications for eligible orders. * Design a user-friendly interface for updating delivery addresses. * Integrate system checks to determine an order's eligibility for address changes based on its current status. * Develop backend logic to update order details and communicate changes to logistics partners. * Ensure customer support is readily accessible for cases where an address change is not possible through the app. |
| US 15 | Cancel Order | As a user, I want to cancel my order before it has started for delivery so that I avoid unwanted orders.  **Acceptance Criteria:**   1. Users can view their order history and select any order that is in a status allowing for cancellation (e.g., ordered but not yet out for delivery). 2. For eligible orders, a "Cancel Order" option is clearly visible and accessible. 3. Upon selecting to cancel the order, the app asks the user to confirm their decision and optionally provide a reason for cancellation. 4. After confirmation, the cancellation is processed immediately, and the user receives a confirmation message or notification indicating the successful cancellation. 5. The app automatically initiates the refund process for the canceled order if payment was already made, adhering to the platform's refund policy. 6. In cases where the order's status does not permit direct cancellation through the app (e.g., order already out for delivery), users are directed to contact customer support for assistance. | **Tasks:**   * Update the order management system to include a cancellation feature for orders not yet out for delivery. * Design and implement a user interface for easy order cancellation within the app. * Integrate a confirmation step to prevent accidental cancellations and gather feedback on cancellation reasons. * Automate the refund process for canceled orders, ensuring transparency and timeliness in returning funds to the user. * Provide clear instructions and support options for orders that cannot be canceled directly through the app. |
| US 16 | Farmer Account Setup | As a fresh farmer, I want to register and log in on the platform so that I can list my products.  **Acceptance Criteria:**   1. A dedicated registration process is available for farmers, distinct from the general consumer registration, to cater to their specific needs. 2. Upon successful registration, farmers receive confirmation and can log in to access their dashboard. 3. The farmer dashboard includes features tailored to product management, order tracking, and access to support resources. 4. Security measures are in place to protect farmer accounts and sensitive information. 5. Login credentials can be recovered or reset through a verified email or phone number to ensure account access continuity. | **Tasks:**   * Design and implement a registration flow for farmers, including verification processes. * Develop a farmer-specific dashboard with functionalities for product listing, order management, and access to resources. * Ensure robust security practices for farmer account registration and login. |
| US 17 | Listing Product Help | As a fresh farmer, I want to receive help to list my products so that I can efficiently reach customers.  **Acceptance Criteria:**   1. The platform offers a step-by-step guide or wizard for listing products, including information on pricing, descriptions, and product categories. 2. Support channels (e.g., chat support, email assistance) are readily available for farmers needing personalized help with their listings. 3. Bulk upload features are available for farmers with multiple products, simplifying the listing process. 4. Guidelines and best practices for product listings are easily accessible to ensure quality and consistency across the platform. | **Tasks:**   * Create a user-friendly interface for product listing, including templates and guides. * Establish dedicated support channels for farmers requiring assistance with listings. * Implement a bulk upload functionality for easy management of multiple products. |
| US 18 | Packing & Shipping Info | As a fresh farmer, I want to access video tutorials for packing so that I can ensure product quality upon delivery.  **Acceptance Criteria:**   1. A library of video tutorials is available, covering topics such as best practices for packing fresh produce, maintaining product freshness during transit, and preparing products for pickup. 2. Tutorials are easily accessible through the farmer dashboard and categorized by product type for easy navigation. 3. Resources are developed in collaboration with agricultural experts to provide reliable and effective packing and shipping methods. 4. Interactive features, such as the ability to ask questions or request specific tutorials, are included to enhance the learning experience. 5. Feedback mechanisms allow farmers to rate and suggest improvements for the tutorials, ensuring the resources remain relevant and valuable. | **Tasks:**   * Curate and develop a comprehensive set of video tutorials focusing on packing and shipping best practices for farmers. * Integrate the tutorial library into the farmer dashboard, ensuring easy access and usability. * Implement interactive and feedback features to engage farmers and continually improve the resource library. |
| US 19 | Delivery Schedule | As a fresh farmer, I want to know the immediate list of products for delivery so that I can prepare orders efficiently.  **Acceptance Criteria:**   1. The farmer dashboard provides a real-time list of products that have been ordered and need to be delivered in the upcoming time frame, organized by order urgency and delivery date. 2. Clear pickup times are displayed for each order, along with any specific instructions from the logistics team or the buyer. 3. Notifications are sent to farmers via their preferred method (app notification, SMS, email) as soon as a new order is placed, including details about the products ordered and the pickup time. 4. The platform allows for easy communication with the logistics team in case of changes in product availability or pickup times. 5. Farmers can confirm their readiness for pickup directly through the dashboard, signaling to the logistics team that products are prepared and ensuring a smooth pickup process. | **Tasks:**   * Integrate a dynamic order management system into the farmer dashboard that updates in real time. * Develop a notification system to alert farmers of new orders and pickup times. * Implement a feature for farmers to communicate with the logistics team and confirm order readiness through the dashboard. * Ensure the system provides detailed information on pickup times, locations, and any specific handling instructions for each order. |
| US 20 | Farmer Dashboard | As a fresh farmer, I want a dashboard for order, sales, and payment management so that I can easily manage my orders and finances.  **Acceptance Criteria:**   1. The dashboard displays real-time updates on order status, including confirmations for products that have been picked up and notifications for any cancelled orders. 2. A summary of recent sales and payment details is prominently featured, showing earnings from completed orders, pending payments, and any adjustments from cancellations. 3. The dashboard provides a breakdown of sales data, including total sales over selectable time periods (e.g., daily, weekly, monthly) and top-selling products. 4. Payment status indicators are included to highlight pending payments, completed transactions, and the expected timeline for any pending earnings. 5. Farmers can access detailed reports on their sales and payment history, with options to export data for their records or further analysis. 6. The platform facilitates easy access to support or contact with the marketplace administration for queries related to payments, pickups, or cancellations. | **Tasks:**   * Design and implement a farmer-specific dashboard that aggregates and displays critical information about orders, sales, and payments. * Develop backend functionalities to process and present real-time data on order status, sales performance, and payment details. * Integrate a reporting feature that allows farmers to view detailed sales and payment histories and export data as needed. * Ensure the dashboard is user-friendly, with intuitive navigation and clear visual indicators for payment statuses and order updates. |
| US 21 | Route Optimization | As a delivery agent, I want my delivery route to be optimized in real-time so that I can make deliveries more efficiently.  **Acceptance Criteria:**   1. The delivery app automatically suggests the most efficient route based on current orders, taking into account real-time traffic data and delivery windows. 2. The app allows manual route adjustments by the delivery agent if needed. 3. Delivery agents receive notifications of any urgent route changes due to unforeseen circumstances like road closures or new urgent delivery requests. 4. Estimated times of arrival (ETAs) are accurately calculated and displayed for each delivery stop. | **Tasks:**   * Integrate real-time traffic data and routing algorithms into the delivery app. * Implement a feature for manual route adjustment. * Develop a notification system for route changes. * Calculate and display ETAs for each delivery. |
| US 22 | Customer Preferences | As a delivery agent, I want to easily access specific delivery instructions so that I can ensure a smooth delivery experience.  **Acceptance Criteria:**   1. Delivery preferences and special instructions from customers are easily accessible within the order details on the delivery app. 2. The app allows for quick communication with the customer in case of clarification needs regarding delivery preferences. 3. Delivery agents can update the delivery status (e.g., delivered, attempted delivery) along with any relevant notes regarding the delivery preferences. | **Tasks:**   * Design an order details section that includes customer preferences and instructions. * Implement a direct messaging or calling feature within the app for communication with customers. * Enable status updates and note additions within the app for each delivery. |
| US 23 | Order Management | As a delivery agent, I want an efficient way to manage my orders in the app so that I can plan pickups and deliveries without confusion.  **Acceptance Criteria:**   1. Delivery agents can view a list of all current day orders assigned to them, with the ability to sort by time, location, or priority. 2. The app provides functionality to mark orders as picked up, in transit, and delivered, with time-stamped records for tracking. 3. Agents can view any changes to their order list in real-time, including cancellations or additional orders. | **Tasks:**   * Create a dashboard or list view of daily orders within the app. * Implement functions to update order statuses with time stamps. * Ensure the order list refreshes in real-time to reflect any changes. |
| US 24 | Report Issues | As a delivery agent, I want to report any issues immediately through the app so that I can resolve problems quickly.  **Acceptance Criteria:**   1. The app includes a feature to report issues directly related to orders, such as missing items or customer complaints, with the option to upload photos or notes. 2. Delivery agents receive immediate feedback or instructions on how to proceed with the reported issue. 3. A record of reported issues and resolutions is accessible to the delivery agent for future reference. | **Tasks:**   * Develop an issue reporting feature within the app, including multimedia upload capabilities. * Integrate an automated response system or direct line to support for issue resolution. * Maintain a log of reported issues and outcomes accessible to the delivery agent. |
| US 25 | Contactless Verification | As a delivery agent, I want to verify delivery completion for contactless deliveries so that I can ensure orders are safely delivered.  **Acceptance Criteria:**   1. For contactless deliveries, the app provides a method to verify delivery completion, such as photo evidence or a unique delivery code. 2. Customers receive a notification confirming the delivery, including any verification evidence. 3. Delivery agents have a simple, quick way to upload or input delivery verification details within the app. | **Tasks:**   * Implement a photo upload feature and/or delivery code input for contactless delivery verification. * Set up automatic notifications to customers upon delivery completion with attached verification. * Design an intuitive interface for verification submission within the delivery process. |

## Scope Validation

Scope validation is an essential phase in the Amazon Fresh Mobile and Web App Development project, ensuring that the completed deliverables align with the defined project scope and address user requirements effectively. This process encompasses several methods of verification:

**Functionality Testing**: Conducted by Chandana Chavatapalem, the Quality Assurance Lead, this step involves thorough testing against technical specifications to ensure all features operate correctly. Functionality testing is planned following each major development phase as detailed in the project schedule, before user acceptance testing (UAT) commences.

**User Acceptance Testing (UAT)**: Orchestrated by Priya Singh, the India Market Strategist, UAT will actively involve a select group of end-users representative of the Indian market. This testing phase is crucial for validating that the app’s functionality resonates with user needs and expectations. UAT will be conducted towards the end of the development cycle, ensuring that any feedback can be integrated before final delivery without impacting the agreed-upon scope.

**Stakeholder Signoff**: Upon successful completion of testing, formal acceptance and signoff will be sought from key project stakeholders. Ravi Kumar, as the India Business Unit Liaison, and Ramu Yanamalachintala, the Program Director, will facilitate this process. Signoff is contingent on all deliverables meeting the predetermined acceptance criteria outlined in the project scope. The signoff process will be a conclusive act that occurs at the end of the UAT phase and prior to the project’s transition to the deployment phase.

These scope validation methods are integrated within the project's timelines and are essential checkpoints for progressing to subsequent phases. By involving the appropriate team members at predetermined times, the project ensures a structured approach to verifying scope adherence, mitigating the risk of scope creep, and confirming that the project outputs will serve the needs of the Indian market effectively.

## Managing Requests for Changes to Project Scope

3.5.1 Scope control is vital for managing changes to the project scope. Using integrated change control, the process for managing scope changes includes:

* **Request Change:** Submission of a detailed change request by any stakeholder.
* **Evaluating Change:** Assessment of the impact, necessity, and feasibility of the proposed change by the project team.
* **Approve or Reject Change:** Decision made by the Change Control Board (CCB) based on the evaluation.
* **Implement Change:** If approved, the change is implemented in the project scope.
* **Close Change:** Formal documentation and communication of the change implementation to all stakeholders.

**3.5.2 Change Control Board (CCB) Members:**

* Ashish Sai Thalla (Project Manager)
* Ramu Yanamalachintala (Program Director)
* Chandana Chavatapalem (Quality Assurance Lead)
* Mounish Kanderi Murali (India Market Strategist)
* Kavita Rao (Lead App Developer)

This Scope Management Plan establishes a structured approach to managing the project's scope, ensuring that the Amazon Fresh Mobile App Development & India Launch project remains aligned with business objectives, regulatory requirements, and user expectations throughout its execution.

# Schedule Management Plan

## Plan Schedule Management

**4.1.1 Introduction**

This section outlines a tailored approach to managing the project's schedule, emphasizing the unique requirements and challenges of rolling out the Amazon Fresh Mobile & Web App in the Indian market. This approach is crafted to ensure on-time delivery while accommodating the dynamic and diverse Indian retail landscape.

**4.1.2 Purpose**

The purpose of this schedule management plan is to establish specific procedures and guidelines adapted to the Amazon Fresh project's context. It aims to synchronize project activities with critical market entry milestones, considering local market dynamics and consumer behaviors in India.

**4.1.3 Inputs**

Key inputs informing this plan include:

* **Project Charter**: Includes specific deadlines critical for the Amazon Fresh launch, considering festival seasons and major shopping holidays in India.
* **Enterprise Environmental Factors**: Considers India's digital infrastructure variability and logistics challenges as significant scheduling influences.
* **Organizational Process Assets**: Utilizes Amazon's repository, enriching it with learnings from previous Amazon launches in similar markets.

**4.1.4 Project Schedule Model Development**

A detailed schedule model will be developed, incorporating key launch phases, from market research to pilot launches in select Indian cities, factoring in the nuances of urban and rural market penetration strategies.

**4.1.5 Scheduling Methodology**

The project will utilize a combination of scheduling methodologies to optimize the timeline management:

* **Gantt Charts**: For visual representation of the project schedule.
* **Critical Chain Method (CCM)**: To manage and allocate project resources efficiently.

**4.1.6 Level of Accuracy and Units of Measure**

Scheduling will account for the intricacies of the Indian calendar, with work hours adjusted to regional variations in public holidays and work culture.

**4.1.7 Control Thresholds**

Control thresholds are set at ±10% variance from the baseline schedule. These thresholds define the limits of acceptable deviation from the planned timeline before corrective or preventive actions are triggered.

**4.1.8 Rules of Performance Measurement**

Performance measurement rules for the project will quantify the completion percentage of project tasks and will utilize Earned Value Management (EVM) to measure and report on project performance.

**4.1.9 Reporting Formats**

Reporting will include customized updates for different stakeholder groups, from Amazon's international team to local market partners, ensuring clarity on progress and challenges specific to the Indian launch.

**4.1.10 Process Descriptions**

The processes will emphasize flexibility and adaptability, with a strong focus on rapid iteration based on consumer feedback and pilot launch data from Indian cities.

**4.1.11 Tools & Techniques**

* **Expert Judgment**: Leverages insights from market experts familiar with India's e-commerce and retail landscapes.
* **Meetings: Engages with local stakeholders and teams in India to refine and adapt the scheduling approach, ensuring alignment with market realities.**

This plan will be regularly reviewed and adapted to meet the evolving needs of the project, ensuring that the Amazon Fresh project's schedule is a dynamic and accurate tool for managing time effectively throughout the project's duration.

## Activities Estimation

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task Identifier | Task Name | Task Description | Duration (Days) | Dependency | Story Points |
| US01-A | Account System Development | Design and implement user registration and login UI; Backend support; Setup email/SMS services. | 8 | - | 13 |
| US01-B | Amazon Account Integration | Integrate login flow with Amazon's existing account management system. | 4 | After Task US01-A | 8 |
| US03-A | Localization Implementation | Implement location detection; Map regions to languages; Design UI for language selection. | 7 | - | 10 |
| US04-A | Personalization Features | Design UI for location-based displays; Backend support for personalized product display. | 7 | After Task US03-A | 10 |
| US05-A | Dynamic Location-Specific Content | Develop system for location-based offers and product listing; Analyze sales data for regional preferences. | 9 | After Task US04-A | 25 |
| US07-A | Festival Features Development | Integrate cultural calendar; Backend support for festival-specific offers and product listings. | 10 | After Task US05-A | 30 |
| US10-A | Enhanced Search Functionality | Develop advanced search capabilities with filters and sorting options. | 6 | - | 18 |
| US11-A | Cart Quantity Selection | Implement UI and backend for selecting product quantities before adding to the cart. | 6 | - | 17 |
| US12-A | Stock Availability Notification | Setup notifications for stock availability; Implement "Notify Me" feature for out-of-stock products. | 5 | After Task US10-A | 13 |
| US13-A | Flexible Payment Integration | Integrate multiple payment methods; Secure handling of payment information. | 9 | After Task US11-A | 26 |
| US14-A | Order Management Improvements | Implement address modification and order cancellation functionalities. | 8 | - | 22 |
| US19-A | Delivery Management System | Develop real-time delivery schedule management; Implement verification for contactless deliveries. | 8 | After Task US14-A | 21 |
| US16-A | Farmer Account and Listing Setup | Design registration flow for farmers; Implement product listing interface with support features. | 11 | - | 28 |
| US18-A | Farmer Support and Dashboard | Develop packing and shipping tutorials; Design farmer dashboard for order and payment management. | 11 | After Task US16-A | 27 |
| US21-A | Delivery Optimization and Preferences | Integrate routing optimization; Design UI for accessing and managing delivery preferences. | 9 | - | 24 |
| US23-A | Delivery Issue Reporting System | Create order management dashboard; Implement issue reporting and resolution feature. | 7 | After Task US21-A | 19 |

## Develop Schedule

## Sprint Schedule

Adopting an Agile framework for the Amazon Fresh project involves focusing on iterative development, where the work is divided into manageable sprints with specific goals.

Given the project end date and starting from 02/18/2024, assuming a two-week sprint cycle, we can organize the sprints and milestones for the Amazon Fresh project. This structure will align with Agile project management practices, focusing on delivering incrementally and iteratively over the project's lifespan.

|  |  |  |  |
| --- | --- | --- | --- |
| Sprint | Dates | Associated Tasks | Goal |
| 1 | 02/18/2024 - 03/03/2024 | Agile Team Formation and Project Kick-off | Establish Agile workflows, team onboarding. |
| 2-3 | 03/04/2024 - 03/31/2024 | Authentication and Account Management Setup | Implement user registration, login, and Amazon integration. |
| 4-5 | 04/01/2024 - 04/28/2024 | Basic Localization and Personalization Features | Develop auto-language setting and content personalization. |
| 6-7 | 04/29/2024 - 05/26/2024 | Location-Based Offers and Content | Deliver location-specific offers and products. |
| 8 | **05/27/2024 - 06/09/2024** | **Alpha Release** | **Test core functionalities with a limited user group.** |
| 9-10 | 06/10/2024 - 07/07/2024 | Festival Offers and Popular Items Integration | Festival-related product features. |
| 11-12 | 07/08/2024 - 08/04/2024 | Enhanced Product Discovery and Management | Advanced search functionalities and cart enhancements. |
| 13 | **08/05/2024 - 08/18/2024** | **Beta Release** | **Wider testing with real users; Gather extensive feedback.** |
| 14-15 | 08/19/2024 - 09/15/2024 | Notifications and Expanded Payment Options | Stock alerts and multiple payment methods integration. |
| 16-17 | 09/16/2024 - 10/13/2024 | Order Modification and Optimized Delivery | Enable order modifications and delivery optimizations. |
| 18-19 | 10/14/2024 - 11/10/2024 | Farmer Platform Enhancement | Launch farmer registration and product management dashboard. |
| 20-21 | 11/11/2024 - 12/08/2024 | Delivery Route Optimization | Implement delivery route optimization. |
| 22-35 | 12/09/2024 - 07/06/2025 | Product Refinement and Market Readiness | Iterative feedback integration and feature enhancement. |
| 36 | **07/07/2025 - 07/20/2025** | **Full Product Launch Preparation** | **Final preparations for the official market launch.** |
| Final | 07/21/2025 - 08/11/2025 | Market Launch | Launch the Amazon Fresh service to the general public. |

**Key Points:**

* **Alpha Release (Sprint 8)**: Focuses on testing core functionalities within a limited user group, aimed at internal stakeholders and selected external users to ensure the app's basic features work as expected.
* **Beta Release (Sprint 13)**: Expands testing to a broader audience, allowing real users to use the app, providing valuable feedback on user experience, feature set, and performance, which will be crucial for the next rounds of iteration.
* **Full Product Launch Preparation (Sprint 36)**: Concentrates on finalizing the app based on feedback from the Alpha and Beta phases, ensuring the product is market-ready, addressing any remaining issues, and ramping up marketing efforts

## Gantt Chart

## Control Schedule

Effective schedule control is essential for the timely and successful delivery of the Amazon Farm Fresh project. This section outlines our approach to monitoring project progress, managing schedule changes, and ensuring alignment with the project's strategic goals. Our control schedule mechanism is designed to be dynamic, responsive, and integrated with the overall project management plan.


**Schedule Monitoring and Adjusting Procedures:**

1. **Regular Progress Reviews:** Conduct weekly progress review meetings with the project team to assess the completion status of scheduled activities, especially focusing on critical path tasks identified in the CPM analysis. Use iteration burndown charts to visualize progress within Agile sprints, enabling immediate adjustments.

**A graph with green lines

Description automatically generated**

1. **Critical Path Analysis:** Continuously monitor and update the critical path based on actual progress and any changes in task dependencies or durations. Special attention will be paid to the tasks within the critical path (US03-A, US04-A, US05-A, and US07-A), ensuring any risks to these tasks are quickly identified and mitigated.



The Critical Path Method (CPM) diagram visualizes the project tasks, their dependencies, and highlights the critical path in red. For the Amazon Farm Fresh project, the critical path based on the dependencies provided is through tasks US03-A (Localization Implementation), US04-A (Personalization Features), US05-A (Dynamic Location-Specific Content), and finally US07-A (Festival Features Development). This path represents the sequence of tasks that directly affects the project's total duration, indicating these tasks are crucial for maintaining the project schedule.

The critical path tasks are:

* **Localization Implementation** (US03-A): Implement location detection, map regions to languages, design UI for language selection.
* **Personalization Features** (US04-A): Design UI for location-based displays, backend support for personalized product display.
* **Dynamic Location-Specific Content** (US05-A): Develop a system for location-based offers and product listing, analyze sales data for regional preferences.
* **Festival Features Development** (US07-A): Integrate a cultural calendar, backend support for festival-specific offers and product listings.

Managing these tasks efficiently is essential to keeping the project on schedule, as delays in any of these activities will directly impact the project completion date

1. **Variance Analysis:** Implement a detailed variance analysis comparing actual progress against the planned schedule at the end of each sprint or major milestone. Analyze variances to identify trends, potential bottlenecks, or areas requiring intervention.
2. **Change Management:** Utilize a formal change management process to evaluate the impact of any proposed changes on the project schedule. All change requests affecting the schedule must be reviewed and approved by the Change Control Board (CCB). Approved changes will be incorporated into the schedule, with necessary adjustments made to the critical path, resources, and completion dates.
3. **Corrective Action and Preventative Measures:** Develop and implement corrective actions in response to identified schedule variances or risks. This may include reallocating resources, adjusting task sequences, or modifying task durations. Preventative measures will be put in place to mitigate future risks to the schedule.

## Level Of Accuracy

The level of accuracy in schedule estimation directly influences the confidence in the schedule baseline. The project will consider an accuracy level within ±10%, with time measured in workdays or hours as applicable to the activity. This accuracy level accommodates slight variances while still mandating investigation if deviations exceed the set parameters.

## Control Thresholds

Control thresholds are established to signal allowable deviations from the schedule baseline. For the Amazon Fresh project, any deviation beyond a 5-day window will necessitate immediate analysis and corrective action. These thresholds ensure prompt responses to potential schedule slippage, maintaining project timing integrity.

## Rules Of Performance Measurement

Performance measurement will be quantified using Tracked Gantt Charts, which will allow for visual tracking of project progress against key deliverables and activities. This method ensures that the project team and stakeholders have a clear understanding of the percentage of work completed and any variances from the planned schedule.

## Reporting Frequency and Formats

The project will produce regular progress reports detailing schedule status. The frequency and formats of these reports will be as follows:

* Weekly progress reports to summarize activities and milestones.
* For Agile methodologies, utilization of sprint reviews, and daily standups to provide continual updates on project progress.

All reporting will be designed to communicate the most accurate and current project timing information to facilitate timely decision-making and stakeholder engagement.

Each section of the schedule management plan outlines a structured approach to maintaining schedule discipline throughout the Amazon Fresh project. By adhering to the described practices, the project aims to deliver outcomes on time, thus upholding stakeholder expectations and project objectives.

# Project Cost Management Plan

## Purpose

The Cost Management Plan outlines the methodology and processes the Amazon Fresh project team will employ to ensure effective planning, estimation, budgeting, and controlling of project costs throughout its lifecycle. It aims to deliver the project within the approved budget while optimizing the use of financial resources.

## Cost Management Planning

**Inputs**

* **Project Charter:** Sets the financial framework, highlighting budgetary constraints.
* **Project Management Plan:** Influences cost estimation through detailed scope and schedule outlines.
* **Enterprise Environmental Factors & Organizational Process Assets:** Provide market insights and historical data critical for informed cost planning.

**Tools and Techniques**

* **Expert Judgment** from seasoned project managers and financial analysts.
* **Data Analysis** techniques, including cost-benefit and reserve analysis, to inform planning and contingency allocation.
* **Meetings** with stakeholders for collaborative plan development and alignment.

**Cost Management Plan Elements** The cost management plan will consist of:

* **Accuracy:** Cost estimates rounded to the nearest $100 for consistency.
* **Contingency Reserve:** Set at 15% of total estimates, reflecting Amazon's risk management strategy.
* **Units of Measure:** Defined across labor, licensing, and operational expenses for clarity.
* **Control Thresholds:** A 10% variance from the baseline cost will trigger a review for corrective action.
* **Performance Measurement:** Bi-weekly reporting using Earned Value Management (EVM) for real-time cost performance insights.
* **Reporting Formats:** Standardized monthly reports ensuring stakeholder visibility.

## Cost Estimation

The Cost Estimation section of the Project Cost Management Plan is instrumental in setting the financial framework for the Amazon Fresh Mobile and Web App Development project. This section outlines the systematic approach for estimating costs that align with the project's objectives and timelines.

**Supporting Detail for Cost Estimation**:

* **Scope Baseline**: The cost estimation adheres to the scope baseline, which encompasses all deliverables and work packages as detailed in the scope management plan.
* **Historic Data**: Leveraging historical cost data from Amazon's past expansions into Europe and Asia offers valuable benchmarks for the current project's cost estimations.
* **Cost Factors**: Comprehensive consideration of various cost factors is integral to the estimation process. This includes labor costs, training expenses, transition costs, maintenance, potential downtime, and potential cost overruns.
* **Contingency Plan**: A contingency plan is established to address resource unavailability and other unforeseen challenges. Alternative strategies and resource options have been outlined to mitigate such risks.

**Assumptions:**

* The project will maintain consistent resource availability and will not experience any significant scope changes.
* Market conditions, especially labor rates, will remain stable during the project lifecycle.

**Constraints:**

* The project operates within a fixed budget, and resources may be limited by external demand and market conditions.

**Estimation Tools and Techniques:**

* **Expert Judgment**: Involvement of subject matter experts who bring knowledge from similar projects.
* **Analogous Estimating**: Applying cost data from past projects to estimate current project costs.
* **Parametric Estimating**: Utilizing statistical modeling to predict costs based on project variables.
* **Bottom-Up Estimating**: Detailing costs from the activity level up to the project total.

**Cost Estimation Table**

|  |  |  |
| --- | --- | --- |
| Phase | Subtotals | % of Budget Before Reserves |
| 1. Requirements Gathering and Analysis | $65,217 | 5% |
| 2. Mobile and Web App Development | $456,522 | 35% |
| 3. AI and ML Integration | $65,217 | 5% |
| 4. Testing and Optimization | $130,434 | 10% |
| 5. Launch and Initial Operations | $65,217 | 5% |
| 6. Project Management | $130,434 | 10% |
| 7. Hardware & Infrastructure | $97,826 | 7.5% |
| 8. Licenses and Services | $130,434 | 10% |
| 9. Training and Support | $65,217 | 5% |
| Subtotal Before Reserves | $1,306,518 | 100% |

**Adding the Contingency Reserve**

* **Contingency Reserve:** $195,652 (15% of $1,304,348 approximated to fit total budget)
* **Total Costs (Including Contingency):** $1,500,000

**Level of Accuracy**

Cost estimations are rounded to the nearest $100, providing a clear guideline for financial planning and ensuring consistency across the project's financial management processes.

**Units of Measurement**

Units used in the estimation process, such as labor hours or licensing fees, are clearly defined to ensure an unambiguous financial tracking and assessment.

**Control Threshold**

The control threshold is set at a 10% variance, aligning with the project's schedule variance policy. Any deviations beyond this threshold will prompt a review and corrective actions.

**Stakeholder Review and Approval**

Upon completion, the cost estimation requires a thorough review and approval by stakeholders. This vetting process is critical to ensure that the cost estimation aligns with stakeholder expectations and can be adopted as the cost baseline for the project.

This Cost Estimation section lays the groundwork for diligent financial management and sets the stage for the subsequent development of a detailed cost baseline that will be used to monitor and control project costs throughout its life cycle.

**Cost Estimation of Software Development (04/09/2024)**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task Identifier | Task Name | Estimated Hours | Cost/Unit or Hour | Budget Allocation | % of Development Budget | Total Costs |
| US01-A | **Account System Development** | **800** | **$75** | **$60,000** | **13.14%** | **$60,000** |
| US01-B | **Amazon Account Integration** | **533** | **$75** | **$40,000** | **8.76%** | **$40,000** |
| US03-A | **Localization Implementation** | **467** | **$75** | **$35,000** | **7.66%** | **$35,000** |
| US04-A | **Personalization Features** | **600** | **$75** | **$45,000** | **9.85%** | **$45,000** |
| US05-A | **Dynamic Location-Specific Content** | **733** | **$75** | **$55,000** | **12.04%** | **$55,000** |
| US07-A | **Festival Features Development** | **800** | **$75** | **$60,000** | **13.14%** | **$60,000** |
| US10-A to US14-A | **Core E-commerce Functionalities** | **1200** | **$75** | **$90,000** | **19.70%** | **$90,000** |
| US16-A & US18-A | **Farmer Account and Support** | **533** | **$75** | **$40,000** | **8.76%** | **$40,000** |
| US19-A, US21-A, US23-A | **Delivery Management Systems** | **667** | **$75** | **$50,000** | **10.95%** | **$50,000** |
| Contingency | **Unforeseen Development Needs** | **-** | **-** | **$21,522** | **4.71%** | **$21,522** |

**Total Allocated for Development (Including Contingency): $456,522**

## Cost Budgeting

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Month / Cost Item | 1-3 | 4-6 | 7-9 | 10-12 | 13-15 | 16-18 | Totals |
| 1. Requirements & Analysis | $32,434 |  |  |  |  |  | $32,434 |
| 2. Mobile & Web App Development | $68478 | $91,305 | $91,305 | $91,305 | 114130 |  | $456,522 |
| 3. AI & ML Integration |  | $19,565 | $13000 | $32652 |  |  | $65,217 |
| 4. Testing & Optimization |  | $19500 | $13000 | $13000 | $13000 | $71934 | $130,434 |
| 5. Launch & Initial Operations |  |  |  | $65,217 |  |  | $65,217 |
| 6. Project Management | $21,739 | $21,739 | $21,739 | $21,739 | $21,739 | $21,739 | $130,434 |
| 7. Hardware & Infrastructure | $32,434 |  |  |  |  |  | $32,434 |
| 8. Licenses and Services | $26000 | $26000 | $26000 | $52,434 |  |  | $130,434 |
| 9. Training and Support |  |  |  |  |  | $65,217 | $65,217 |
| Subtotals (Pre-Reserve) | $643,565 | $86,956 | $152,173 | $86,956 | $152,173 | $86,956 | $1,304,348 |
| Contingency Reserve | $32,913 | $4,348 | $7,609 | $4,348 | $7,609 | $4,348 | $195,652 |
| Total Monthly Cost | $676,478 | $91,304 | $159,782 | $91,304 | $159,782 | $91,304 | $1,500,000 |

## Cost Control

In the Amazon Fresh Mobile and Web App Development project, cost control is not merely a procedural necessity; it's a strategic endeavor that ensures every dollar spent contributes directly to delivering value. This section outlines our hands-on approach to overseeing expenditures, dynamically adjusting to project evolutions, and maintaining transparency with all stakeholders.

**Activities in Cost Control**

* **Weekly Expenditure Reviews:** Every Monday, our project management team will review the previous week's expenses against the project's cost baseline. This allows for real-time identification of variances and immediate corrective actions if necessary.
* **Monthly Cost Baseline Updates:** On the first of each month, we'll conduct a comprehensive review of our cost baseline in relation to actual spend and project progress. This ensures our budget reflects the latest project insights and external factors, such as market rate changes for resources.
* **Change Control Board (CCB) Meetings:** Scheduled bi-weekly, the CCB will evaluate any proposed changes impacting the budget. These meetings are critical for integrating cost control with the broader change management process, ensuring any budget adjustments are thoroughly vetted and approved.
* **Stakeholder Dashboards:** Utilizing PMIS, we will maintain up-to-date dashboards that provide stakeholders with instant access to financial data, including variances and the status of corrective actions. This promotes transparency and facilitates informed decision-making.

**Tools and Techniques for Cost Control**

* **Expert Panels:** We will convene monthly panels comprising financial experts and senior project managers to share insights and refine our cost control practices, ensuring alignment with industry best practices and project realities.
* **Data-Driven Analysis:** Our PMIS will be configured to automatically generate variance, trend, and reserve analysis reports. These reports, reviewed during our weekly expenditure reviews, will inform our cost control decisions and forecasts.
* **EVM Integration:** We'll employ Earned Value Management (EVM) techniques, including the calculation of the To-Complete Performance Index (TCPI), to not just track cost performance but also to forecast the project's financial trajectory. This will be a cornerstone of our monthly cost baseline updates.

**Maintaining the Cost Baseline**

* **Dynamic Budget Adjustments:** Recognizing the agile nature of our project, we'll embrace flexibility in our budgeting. Adjustments to the budget will be made in response to validated learnings from sprints and stakeholder feedback, always with an eye towards maximizing project value.
* **Stakeholder Involvement in Budget Revisions:** All budget adjustments will be communicated through bi-weekly newsletters and detailed in our monthly stakeholder meetings. This ensures every stakeholder is informed of and understands the rationale behind budget changes.

Effective cost control in the Amazon Fresh project is about agility, transparency, and collaboration. By actively involving the project team and stakeholders in the financial oversight of the project, we ensure a collective commitment to financial integrity and the successful delivery of the project within its budgetary framework. Through these practices, we align our financial trajectory with the strategic objectives of the project, ensuring that we deliver not just a product, but value to our stakeholders and customer

# Project Staffing Management Plan

This table serves as a foundation for staffing the Amazon Fresh project, outlining key roles crucial for the project's success. It's adaptable based on project evolution, ensuring that staffing strategies remain aligned with project needs and goals. Adjustments to roles, responsibilities, or required skills might be necessary as the project progresses, emphasizing the importance of flexibility and responsiveness in staffing management.


|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Roles | Responsibilities | Required Skills | Sourcing Avenues | Training Needs | Supervision Mechanisms |
| Project Leader | Leading the project team to meet the project goals within specified scope, schedule, and budget. | - Project management - Leadership  - Strategic planning | Amazon | - Compliance requirements for foreign business in India  - Data privacy policy in India  - India fresh market overview | - Weekly written reports - Monthly status reports  - Jira for progress tracking and communication |
| Technical Lead | Guiding the technical team in architecture design and technology decisions. | - Software development  - Architectural design - Agile methodologies | Amazon | - Technology stack updates  - Agile development practices  - Security best practices | - Daily stand-ups  - Sprint planning and review meetings - Code review sessions |
| UI/UX Designer | Designing intuitive and engaging user interfaces and experiences. | - UI/UX design principles  - Prototyping tools  - Graphic design | In-house/Contract | - Design thinking workshops  - Accessibility standards - Prototyping tools updates | - Design review sessions  - Usability testing |
| QA Engineer | Ensuring product quality through comprehensive testing strategies. | - Automated/manual testing  - Test planning  - Bug tracking systems | In-house/New Recruitment /Contract | - Automated testing tools - Performance/load testing techniques | - Regular test case reviews  - Bug triage meetings |
| Market Analyst | Analyzing market trends and consumer needs to inform product development. | - Market research  - Data analysis  - Competitive intelligence | In-house/New Recruitment | - Advanced analytics tools  - Consumer behavior analysis  - Market segmentation techniques | - Weekly insights reports  - Strategic planning sessions |
| Operations Manager | Overseeing operational, logistical, and regulatory aspects within the target market. | - Operations management  - Regulatory compliance  - Vendor management | Amazon/New Recruitment | - Local supply chain dynamics  - E-commerce regulations in India  - Vendor negotiation skills | - Operations review meetings  - Vendor assessment reviews |
| Developer (Front-end/Back-end) | Building and maintaining the software product in line with design and specifications. | - Relevant programming languages  - Frameworks and libraries  - Version control systems | Contract/New Recruitment | - Project-specific development frameworks - Code optimization techniques  - Security in software development | - Sprint retrospectives  - Peer programming reviews |
| Customer Support Specialist | Addressing customer inquiries and feedback, and liaising with the development team to improve the product. | - Customer service skills  - Technical product knowledge  - Communication skills | In-house/Contract/outsourced | - Product functionality deep dive  - Customer relationship management tools  - Conflict resolution skills | - Customer feedback sessions  - Support ticket analysis |
| Data Scientist | Analyzing user data to drive product improvements and personalization. | - Data modeling  - Machine learning  - Statistical analysis | In-house/Contract | - Machine learning models  - Big data analytics tools - Privacy and ethical data use | - Bi-weekly data insights sharing - Model performance review sessions |
| Content Strategist | Developing and executing content strategies to engage users and support SEO. | - Content development  - Search Engine Optimization  - Social media management | In-house/Contract | - SEO trends and tools - Content marketing strategies  - Social media analytics | - Content review meetings  - SEO performance reviews |
| Security Analyst | Ensuring the product and user data are protected against cyber threats. | - Cybersecurity principles  - Risk assessment  - Incident response | Amazon/New Recruitment | - Latest cybersecurity trends  - Compliance and regulatory standards - Security analysis tools | - Security audits  - Incident response drills |
| Agile Coach | Guiding the team in Agile practices to improve project delivery efficiency. | - Agile methodologies - Coaching and mentorship  - Team dynamics | Contract | - Advanced Agile methodologies  - Team facilitation techniques  - Continuous improvement practices | - Agile practices workshops  - Sprint reflection sessions |

## Organization Chart

A diagram of a company

Description automatically generated

## Resource Histogram



# Quality Management Plan

## Quality Objective

* **Seamless User Experience:** Design a highly intuitive and responsive mobile shopping application, with a focus on personalization for the Indian market. Prioritize multilingual support and diverse payment options.
* **Uncompromised Performance:** Ensure the app demonstrates stability and consistent performance across varying network conditions to maximize accessibility for all users.
* **Robust Data Security:** Implement stringent data security measures exceeding industry standards to protect sensitive user and transaction information.
* **Intelligent Recommendations:** Utilize AI-powered algorithms to provide tailored product suggestions, enhancing user experience and driving sales conversions.
* **Ethical Sourcing:** Establish direct sourcing relationships with local farmers and suppliers, guaranteeing product freshness and supporting regional economies.

## Quality Management Planning

* **Agile Approach:** Employ an iterative and adaptive Agile methodology to quality management throughout the project lifecycle.
* **Customer Focus:** Integrate customer feedback and satisfaction metrics as core drivers of quality improvements at all development stages.
* **Cross-Functional Collaboration:** Foster a collaborative environment where development, testing, and business stakeholders work together to ensure quality is embedded within the product.
* **Metrics-Driven:** Maintain clearly defined quality metrics (outlined in the next section) to track progress, measure success, and identify areas for continuous improvement.

## Key Quality Areas & Metrics

|  |  |  |
| --- | --- | --- |
| Quality Area | Quality Standards | Metrics |
| Registration and Login | Efficient, secure, and user-friendly registration/login process. | Success rate (99%), Response time (<2 sec), Confirmation rate (98% within 5 min), Customer satisfaction (4.5/5) |
| Localization and Personalization | Accurate language adaptation, content tailored to user demographics and location preferences. | Language setting accuracy (95%), Positive user feedback on localization (90%), Increased engagement (20% higher CTR) |
| Performance Optimization | Consistent app stability & responsiveness across all network conditions. | Crash rate (<0.1%), Action response time (95% of actions <3 sec) |
| Secure and Varied Payment Options | Integration of secure, reliable, and diverse payment gateways. | Transaction success rate (99%), Zero security breaches, User satisfaction with payment options (90%) |
| Order and Delivery Management | Accurate order processing, real-time updates, reliable on-time deliveries. | Order accuracy (99.5%), Effective stock notifications (95% user satisfaction), On-time delivery rate (98%) |
| Festivals and Cultural Promotions | Timely, culturally relevant promotions, personalized offers & recommendations. | Sales conversion increase (25% during promotions), User engagement with festival content (50% of logged-in users) |
| Product Searching and Listing | Accurate search, intuitive sorting/filtering, visually appealing product listings. | Search accuracy (90%+ user rating), Search speed (<1 sec ), Product presentation (customer feedback-driven) |
| Farmer and Supplier Integration | Streamlined platform for farmer onboarding, product listing, and order management. | Farmer onboarding success (95%), Farmer satisfaction (4/5), Product freshness (customer feedback-driven) |
| Delivery Agent Efficiency | Optimized routing, clear instructions, seamless in-app order management. | Delivery time reduction (15%), Delivery agent satisfaction (4/5) |

## Quality Managing

**Quality Assurance with Continuous Improvement**

**Kaizen and Lean Methodologies:**

* Apply Kaizen by inviting constant, incremental improvements from our agile teams, particularly after each sprint review.
* Use Lean principles to identify and eliminate waste in processes, focusing on activities that add value to our stakeholders in the Indian market.
* Implement Kanban to visualize workflows for the development and launch phases, ensuring clarity and efficiency.

**Benchmarking for Excellence:**

* Regularly benchmark against Amazon Fresh's successful launches in Singapore and Japan, drawing lessons to fine-tune our strategy for the Indian market.
* Analyze performance metrics and customer feedback from these regions to set high but attainable goals for our platform.

**Quality Audits for High Standards**

**Scheduled Quality Audits:**

* Conduct regular quality audits, led by our Quality Assurance Lead, Chandana Chavatapalem, to verify adherence to the project’s high standards and Agile practices.
* Perform these audits at the end of each sprint, assessing documents, code, and testing procedures against our defined acceptance criteria and industry best practices.

**Iterative Testing and Review:**

* Audits will involve thorough reviews of the registration process, localization features, and AI-powered recommendation systems, ensuring they meet the specific needs of the Indian market as reflected in our user stories.
* Testing processes will be examined to confirm comprehensive coverage and effective defect management, especially considering the regional diversities in India.

**Change Control and Client Satisfaction:**

* Assess the efficiency of our change control processes to ensure that scope creep is managed and that any changes are properly documented and communicated.
* Include feedback from pilot users to gauge satisfaction and quality perceptions, directly linking to our success criteria like user adoption rates and app performance.

**Corrective Actions and Continuous Improvement:**

* Post-audit, the project team will be responsible for implementing corrective actions swiftly to remedy any identified quality issues.
* Encourage a culture of continuous improvement, using audit outcomes to refine processes and enhance the quality of the Amazon Fresh India project.

**Integration with Agile and Local Focus**

* Weave the quality management initiatives with the Agile methodology that underpins the project, emphasizing responsiveness to the feedback from sprints and reviews.
* The Quality Management Plan will be deeply integrated with the localized approach of the project, ensuring all features from multilingual support to payment methods are not just functional but also resonate with the Indian users’ preferences and behaviors.

By aligning the Managing Quality section closely with the project’s strategic initiatives, like the integration with local suppliers and adherence to Indian cultural nuances, the Amazon Fresh India project stands to not only meet but exceed quality expectations, providing an unparalleled online grocery shopping experience tailored to the Indian market.

## Quality Controlling

The Amazon Fresh India project will utilize statistical sampling to ensure the representativeness of user satisfaction data across various stakeholder groups. This methodology enables data-driven quality control and informs continuous improvement initiatives.

**Sampling Methodology**

* **Formula:**

Sample Size = 0.25 \* (Certainty Factor / Acceptable Error)²

**Confidence Levels & Sample Sizes:**

|  |  |  |  |
| --- | --- | --- | --- |
| Segment | Certainty Level | Certainty Factor | Sample Size |
| Shoppers | 95% | 1.96 | 384 |
| Suppliers | 90% | 1.645 | 169 |
| Administrators | 80% | 1.281 | 41 |

**Rationale**

* **Shoppers:** A high confidence level (95%) is essential for shopper satisfaction, as it directly impacts business metrics.
* **Suppliers:** A 90% confidence level is appropriate for supplier feedback, allowing us to assess partnership effectiveness.
* **Administrators:** An 80% confidence level is suitable for administrators due to their smaller user group size and the system's internal nature.

**Considerations**

* **Sampling Technique:** The project may use stratified random sampling to ensure demographic and regional diversity within samples.
* **Data Collection:** A combination of surveys, in-app feedback mechanisms, and focus groups will be used to gather quantitative and qualitative data.

## Testing Methods

Testing is not a phase that comes at the end of product development but is an integral part of every stage of the systems development lifecycle (SDLC), particularly within the Agile framework that we have adopted. In our project, testing commences with the delivery of the first sprint and continues iteratively throughout the SDLC.

**Sprint Testing:**

* **Sprint 1 Testing (Starting 02/18/2024):** The initial sprint focuses on establishing Agile workflows and onboarding the team. Testing at this stage involves validating the environment setup, tool configurations, and ensuring the Agile workflows are functioning as intended.
* **Sprint 2-3 Testing (Starting 03/04/2024):** As we move into setting up authentication and account management, testing will cover all login and registration features, with a focus on the secure integration of Amazon's existing account management systems.
* **Subsequent Sprints:** Each sprint thereafter, as per the project schedule, includes a "Test" phase, where the developed features are rigorously examined. This ensures that as new features are added, they are tested in conjunction with existing functionalities to maintain system integrity and performance.

**Types of Testing:**

* **Unit Testing:** Each individual component, such as the account registration and product search features, is tested to ensure they function correctly in isolation.
* **Integration Testing:** Post-unit testing, we verify that functionally grouped components, such as the delivery notification process, work together as intended.
* **System Testing:** We conduct system testing as one entity to ensure all components of the system work together seamlessly.
* **User Acceptance Testing (UAT):** This independent testing is performed by end-users and is crucial for confirming that the developed system meets all user requirements before the final deployment.

**Iterative Testing Techniques:**

* **Alpha and Beta Testing:** Alpha testing will occur in Sprint 8, while Beta testing is scheduled for Sprint 13, allowing us to refine the system with feedback from real users in a controlled environment.
* **Performance/Stress Testing:** To ensure the system can handle the expected load, we will conduct stress testing by simulating an increase in concurrent users from 10,000 to 100,000.
* **Scalability Testing:** Regular scalability testing ensures the system can grow with the user base and handle the increased load without degradation in performance.

**Quality Assurance Beyond Testing:**

* We adhere to Watts S. Humphrey's definition of a software defect and strive to ensure that there are no potential defects when we enter system testing. This requires developers to be responsible for providing error-free code at each stage of testing, fostering a culture where quality is everyone's responsibility.

Testing will be overseen by our Quality Assurance Lead, Chandana Chavatapalem, with the objective to not only detect and fix defects but also prevent them from occurring in the first place. The feedback loop from each testing phase will inform the subsequent development and testing cycles, ensuring continuous improvement and alignment with project objectives.

## Problem Reporting & Correction

**During Agile Ceremonies:**

* + **Sprint Planning**: Any potential quality issues anticipated during upcoming sprints will be discussed and mitigation strategies will be planned.
  + **Daily Stand-ups**: Team members will report any immediate quality concerns encountered during their tasks.
  + **Sprint Reviews**: At the end of each sprint, any quality issues encountered will be presented to stakeholders, including deviations from the acceptance criteria outlined in the user stories.
  + **Sprint Retrospectives**: The team will reflect on quality issues from the completed sprint, identifying root causes and action items to prevent recurrence.
  + **Quality Issue Log**: A dedicated log will be maintained by the Quality Assurance Lead, Chandana Chavatapalem, to document all identified quality problems, their impact, and the status of resolutions.

**Correction Mechanism**

* **Backlog Refinement**: All identified quality issues will be added to the project backlog and categorized based on their urgency and impact. These will be prioritized for resolution in subsequent sprints.
* **Task Allocation**: Specific tasks to address quality issues will be assigned during sprint planning, ensuring they are addressed in a systematic and timely manner.

**Form and Frequency of Reporting**

* **Weekly Quality Reports**: A weekly report will be compiled, highlighting new quality issues, progress on existing ones, and any impact on project metrics.
* **Sprint Quality Review**: A detailed quality review will be part of each sprint review meeting, where all stakeholders can examine the progress on quality issues and their resolution.

**Integrated Change Control**

* **Change Control Board (CCB)**: Any quality issue that potentially impacts the project's scope, schedule, or cost will be escalated to the CCB. The CCB will review the issue, assess the impact, and approve or reject changes. The members of the CCB as per your PMP are Ashish Sai Thalla, Ramu Yanamalachintala, Chandana Chavatapalem, Mounish Kanderi Murali, and Kavita Rao.
* **Formal Review Process**: A change request form will be used to detail the issue, proposed changes, and impacts on the project. This form will be submitted to the CCB for review.
* **Stakeholder Approval**: If the change affects the project baselines, formal approval from stakeholders will be required. This ensures transparency and that all parties are aligned with the modifications to the project plan.

**Continuous Improvement**

* **Quality Improvement Backlog**: A separate backlog for continuous quality improvement ideas will be maintained. This ensures that the project continuously evolves and integrates lessons learned from quality issues.
* **Agile Learning**: Insights from the resolution of quality issues will be used as learning opportunities to improve the team’s Agile practices and performance.

By using these mechanisms, the Amazon Fresh India project will maintain high standards of quality management, ensuring that all identified issues are systematically addressed and that the project can adapt to changes while maintaining stakeholder alignment and project integrity.

# Risk Management Plan



## Risk Register for Amazon Fresh Project

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status |
| R01 | High | Technology Stack Incompatibility | The chosen tech stack may not meet all project requirements | Technical | Inadequate research | New requirement discovery | Re-evaluate and update tech stack; conduct feasibility studies | Technical Lead | Medium | High | Open |
| R02 | Med | Scope Creep | The scope of the project may grow without proper checks | Scope Management | Lack of clear initial requirements | Requests for additional features | Strict change control process; stakeholder engagement | Project Manager | High | Med | Monitored |
| R03 | High | Regulatory Compliance Issues | The app may face compliance issues with local regulations in India | Legal | Unforeseen regulatory changes | Legislative updates | Legal review; compliance audits; contingency planning | Legal Advisor | Low | High | Open |
| R04 | Low | Market Misalignment | The product may not align with the target market needs | Market | Insufficient market research | Customer feedback | Market research; pivot strategy; feature adjustment | Market Analyst | Low | Med | Open |
| R05 | Med | Budget Overruns | The project expenses may exceed the forecasted budget | Financial | Misestimation of costs | Cost variance in reporting | Cost control measures; regular budget reviews | Financial Officer | Medium | High | Open |
| R06 | High | Data Privacy Breach | User data could be compromised due to security vulnerabilities | Security | Software vulnerabilities | Security incident reports | Security audits; implementation of enhanced security protocols | Security Analyst | Medium | High | Open |
| R07 | Med | Resource Turnover | Key project personnel may leave the project unexpectedly | Human Resources | Lack of engagement; competitive job market | Resignation notices | Succession planning; cross-training; retention strategies | HR Manager | Medium | Med | Open |
| R08 | Low | Technology Obsolescence | Adopted technologies may become outdated during the project | Technical | Rapid technological advancement | Release of new technologies | Regular technology reviews; flexible architecture | Technical Lead | Low | Med | Open |
| R09 | High | Integration Failures | Third-party services may not integrate well with the project system | Technical | Complex service interfaces | Integration testing failures | Pre-integration testing; alternative solution exploration | Technical Lead | High | High | Open |
| R10 | Med | User Adoption Hurdles | Users may be reluctant or slow to adopt the new app | Market | Resistance to change | Low initial user metrics | Marketing campaigns; user incentives; feature revisions based on feedback | Marketing Manager | High | Med | Open |

**Note:**

* **Rank** is determined by assessing the probability and impact of each risk; High/Medium/Low helps in prioritizing risk responses.
* **Probability** and **Impact** are assessed on a scale (e.g., High/Medium/Low), indicating the likelihood of the risk occurring and the potential effect on the project.
* **Status** can be "Open", "Monitored", "Closed", or other relevant terms indicating the current state of the risk.

# Communication Management Plan

## Stakeholder Communication Requirements

* **Project Leader**

The Project Leader orchestrates the project, ensuring all deliverables and timelines align with the project's goals. Initially, the Project Leader engages in strategic planning with the senior management to outline the project scope and resource needs, using tools like Jira to track progress and ensure visibility across teams. Weekly meetings with the project management team and monthly cross-departmental sessions ensure consistent alignment and timely decision-making. Any significant updates or deviations are communicated through special sessions, and feedback is systematically incorporated into project planning documents and Jira.

* **Technical Lead**

The Technical Lead oversees the technical development of the Amazon Fresh India apps. Starting with system architecture development in collaboration with the UI/UX and Development teams, this role requires daily stand-ups to ensure alignment on technical issues and sprint goals. Technical architecture and updates are reviewed in weekly technical meetings and bi-weekly sprint reviews. Feedback from these sessions influences ongoing development efforts and is tracked using Jira and documented in technical review documents.

* **UI/UX Designer**

The UI/UX Designer is tasked with designing intuitive and engaging user interfaces for the mobile and web apps. The process begins with gathering initial design requirements from the Market Analysts, followed by iterative design sessions. Weekly design review meetings allow for the refinement of designs based on team feedback and usability testing results, which are crucial during major project milestones. All design documents and feedback are managed through Jira and shared via email updates to ensure stakeholders are kept in the loop.

* **QA Engineer**

QA Engineers ensure that both the mobile and web apps meet the established quality standards. The role begins with defining test plans, which are reviewed in weekly QA meetings. Daily stand-ups with the Development team help to address immediate testing needs and bug fixes, ensuring quick communication of issues via Jira. Regular bug triage sessions help prioritize issues for resolution, and feedback from these sessions is documented in detailed test reports.

* **Market Analyst**

Market Analysts provide insights into market trends and consumer needs that inform the product development process. They conduct initial market research and share findings in weekly market analysis meetings. As the project progresses, they continue to gather feedback, which is discussed in strategic planning sessions. All market insights and consumer feedback are tracked through Jira, with critical insights communicated via email to ensure prompt consideration by the project team.

* **Operations Manager**

The Operations Manager handles logistical and operational aspects, initiating the project lifecycle with a review of supply chain logistics and vendor management strategies. Weekly operations meetings allow for ongoing review of logistical challenges and updates. Additional sessions with vendors and supply chain partners are held as needed to address emerging issues, with key updates and feedback managed through Jira and communicated via email to relevant stakeholders.

* **Developer (Front-end/Back-end)**

Developers are integral from the initial coding phase, with daily stand-ups to discuss development progress and sprint goals. They engage in peer programming reviews and sprint retrospectives, held bi-weekly, to ensure coding standards and project requirements are met. Feedback from these sessions is used to refine development processes, documented in Jira, and reviewed during sprint planning sessions.

* **Customer Support Specialist**

Customer Support Specialists engage with customers from the early stages of launch, managing inquiries and feedback through daily support sessions. Weekly support meetings help address broader customer service issues and strategies for improvement. Feedback from these sessions is analyzed during support ticket reviews, with critical issues escalated and documented in Jira for action by the development team.

* **Data Scientist**

Data Scientists analyze user data to drive product improvements. They start by setting up data collection frameworks, then share bi-weekly data insights in dedicated sessions. Model performance is reviewed regularly, with critical analyses discussed in strategic sessions to influence product direction. Feedback and data models are managed through Jira, ensuring alignment with development and marketing strategies.

* **Content Strategist**

The Content Strategist develops and executes content strategies to enhance user engagement. Initial content plans are refined through weekly content meetings, with additional reviews during major project phases to ensure content aligns with SEO and marketing goals. Performance feedback from these sessions is used to adjust strategies and is tracked via Jira and communicated through email updates.

* **Security Analyst**

Security Analysts start by establishing security protocols and compliance measures. Weekly security meetings and incident response drills ensure the team is prepared and the apps remain secure. Feedback from these drills and ongoing security audits are documented and reviewed in Jira, with significant findings communicated to the technical team and management to ensure immediate action.

* **Agile Coach**

The Agile Coach facilitates the adoption of Agile practices across teams, starting with initial training sessions and continuing through daily stand-ups and sprint planning sessions. Feedback from sprint retrospectives and Agile workshops is used to refine team dynamics and improve efficiency, with key learnings documented in Jira and shared in regular coaching sessions.

## Communication Summary

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Stakeholders (Receivers)** | Communications Name | Communication Method | Producers | Communication Frequency |
| Project Steering Committee | Weekly status meeting | Short meeting, Jira, and email updates | Mounish Kanderi (Project Leader) | Weekly, every Monday at 9 AM |
| **Sponsor and Champion** | Monthly status meeting | Short meeting, Jira, and email updates | Mounish Kanderi (Project Leader) | First Thursday of each month at 10 AM |
| **Technical Team** | Daily stand-ups | Short meetings and Jira for progress tracking | Kavita Rao (Lead App Developer) | Daily, every morning at 10 AM |
| **UI/UX Team** | Weekly design reviews | Short meetings, email updates, and Jira | Arjun Patel (UX/UI Design Lead) | Weekly, every Friday at 3 PM |
| **QA Team** | Weekly QA meetings | Short meetings and Jira for tracking | Chandana Chavatapalem (Quality Assurance Lead) | Weekly, every Thursday at 2 PM |
| **Marketing and Customer Support Teams** | Bi-weekly market analysis meetings | Email and project management tools | Priya Singh (India Market Strategist) | Bi-weekly, every other Wednesday at 2 PM |
| **Operations Team** | Weekly operations meetings | Email and Jira for progress tracking | Ashish Sai Thalla (Logistics & Supply Chain Lead) | Weekly, every Tuesday at 4 PM |
| **Cross-Functional Teams** | Sprint planning sessions | Short meetings, sprint retrospectives, and Jira | Mounish Kanderi (Project Leader) | Weekly sprint planning, every Tuesday at 11 AM |